## Sheet1
Risk no. | Description | Evaluate | Likelihood | Level of impact | Responsibilty | Response | Control Measures
1 | Database not working. | Mysql when run crashes | Low | High | MySql | Drop the database and use the schema create the database again | Create backups of the database and saved the schema.
2 | non-functioning product deployed | Product could have issues that affect perfomance or runability. | Medium | High | Development team | Depend latest stable version | Do Thorough testing before implentation and deployment.
3 | Internet service down | No access to internet means productivity goes down. | Low | Medium | Manager | Use tethering to gain access to internet via phone data until primary internet service is back online. | Acquire stable internet.
4 | Github branch merges to wrong branch | Potential loss of data due to merge replaceing file and folders. | Low | High | Development team | Revert back to previous commit and merge branch with the branch. | Keep to git principle and review any pull,push and merge before confirming.
5 | Requirement not achieved. | The product does not fullfill its purpose due to lack of requirement achieved. | Medium | High | Development team | Use project management tools such as jira or Monday to keep track of the product development lifecycle. | Confirm if the requirement are achievable within the timeframe and focus on high priority requirments.